## Tabelle1
Activity | Duration (weeks) | Start Date | End Date | Dependencies | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27
Kickoff Meeting | 1 | 2025-07-01 | 2025-07-08 | bar: Week 1
Requirements Gathering | 2 | 2025-07-09 | 2025-07-23 | Kickoff Meeting | bar: Week 2 to Week 3
UI Design | 3 | 2025-07-24 | 2025-08-14 | Requirements Gathering | bar: Week 3 to Week 5
Prototype Development | 4 | 2025-08-15 | 2025-09-12 | UI Design | bar: Week 5 to Week 8
Core Game Development | 6 | 2025-09-13 | 2025-10-24 | Prototype Development | bar: Week 8 to Week 13
AR Development | 5 | 2025-10-25 | 2025-11-27 | Prototype Development | bar: Week 13 to Week 17
Testing & Debugging | 4 | 2025-10-28 | 2025-12-25 | Core Game Development, AR Development | bar: Week 17 to Week 20
User Feedback & Iteration | 3 | 2025-12-26 | 2026-01-25 | Testing & Debugging | bar: Week 20 to Week 22
Final Polishing | 2 | 2026-01-16 | 2026-01-29 | User Feedback & Iteration | bar: Week 22 to Week 23
Deployment & Launch | 2 | 2026-01-30 | 2026-02-12 | Final Polishing | bar: Week 23 to Week 24
Maintenance & updates | Ongoing | 2026-02-13 | Ongoing | Deployment & Launch | bar: Week 25
Costs and Pricing
Development Costs
| Qty | Salary | Months | Total
Developer | 4 | 12500 | 3 | 150000
UI Designer | 1 | 10000 | 3 | 30000
Tester | 1 | 10000 | 2 | 20000
Project Manager | 1 | 12500 | 4 | 50000
Equipment (License, Hardware) | 1 | 10000 | 4 | 10000
Total Development Costs |  |  |  | 260000
Marketing Costs
Marketing / Advertising |  |  |  | 30000
Launch event |  |  |  | 20000
Total Marketing Costs |  |  |  | 50000
Operational Costs
| Qty | Costs | Months | Total
Infrastructure | 1 | 5000 | 6 | 30000
Maintenance and support | 1 | 5000 | 6 | 30000
Total Operatinal Costs |  |  |  | 60000
Estimated Costs |  |  |  | 370000
Pricing | Downloads | Revenue
10 | 50000 | 500000